## Sheet1
Priorities | Tasks | 2016-10-06 | 2016-10-13 | 2016-10-20 | 2016-10-27 | 2016-11-03 | 2016-11-09 | 2016-11-16 | 2016-11-23 | 2016-11-30 | 2016-12-07 | 2016-12-14 | 2016-12-21 | 2016-12-28 | 2017-01-04 | 2017-01-11 | 2017-01-18 | 2017-01-25 | 2017-02-01 | 2017-02-08 | 2017-02-15 | 2017-02-22 | 2017-03-01 | 2017-03-08 | 2017-03-15 | 2017-03-22 | 2017-03-29 | 2017-04-05 | 2017-04-12 | 2017-04-19 | 2017-04-26 | 2017-05-03
Critical Tasks = In RED
1= min | Assessment 1
5= max | Requirements Report
5 | Meet with client several times to learn of requirements (requirement elicitation)
4 | Ask client to clarify several requirements and tasks
3 | Send Questions to University of York Communications Office
5 | Split requirements into functional and non-functional
3 | Send out a survey to obtain data on usefulness of several requirements/ justification
Architecture Report
5 | Determine tool used
3 | Analyse requirements and determine UML design based on Requirements and remit
4 | Finalise UML design
4 | Write report on expected class structure and character design
Methods Report
5 | Determine how we want to organise the team and justify this
4 | Determine what development method we want to use
2 | Determine what tools we can use to aid development
3 | Determine which tools we should use out of the list of options we have
4 | Write a report on all of this and why we chose to use certain tools over others
3 | Determine the development strategy to be used in future assessments
3 | Develop a realistic schedule for completion of future assessments
4 | Create a gantt chart showing this schedule
Website
4 | Determine website design
2 | Determine tools and methods used to develop website
5 | Develop website with links to all our work so far
| Assessment 2 | [5 empty] | a
| Implementation | [5 empty] | x | [8 empty] | x
5 | Determine part of game to fully implement
4 | Begin coding based on architecture design + class design
3 | Write document on requirements not fully implemented
2 | Develop a manual on features currently implemented
2 | Create executable for game and zipfile containing code
1 | Determine relevant URLs and reference them
Architecture Report
4 | Plan structure of codebase
4 | Finalise technology choices, including language and tools
3 | Produce architecture documentation
3 | Document justification of chosen architecture
GUI Implementation
4 | Finalise map layout and design of rooms
3 | Finalise character design
4 | Used "Tiled" to create a map
2 | Create top-down sprites of characters in dif. positions
3 | Customize the map
3 | Implement keyboard functionality
GUI Report
3 | Summarise GUI
2 | Analyse usability reasons for implementation decisions
2 | Justify GUI based on requirements
2 | Justify GUI based on playability
1 | Reference relevant websites for justification and research
Testing + Testing Report
4 | Prepare a list of tests that are run whenever a significant change is implemented
4 | Create automatic logs of tests
3 | Summarise testing methods
3 | Justify why testing methods are appropriate
3 | Compile statistics of test success and failure and create charts
4 | Give reasons for failed tests
5 | Study for Exams
Update Website
2 | Convert all documents to PDF format
3 | Upload all new work done
Assessment 3
Change Report
4 | Analyse methods, risks, requirements used in new project
4 | Determine team's approach to change management
5 | Update requirements and architecture and justify changes
3 | GUI Report
4 | Update testing report with updated testing methods and justify changes
2 | Update methods and future assessment plans
3 | Update Risk Assessment and Mitigation report and justify changes
Implementation and Report
4 | Analyse code used in new project and determine changes to be made
5 | Update code to meet new requirements
2 | Explain how code meets updated requirements
2 | Report on changes made to software and justify these
4 | Update Website
Assessment 4
Implementation
4 | Ensure the game and requirements so far meet the remit
4 | Determine what needs to be added to the game for all requirements to be met
3 | Determine what changes need to be made based on updated architecture
5 | Determine class structure and design for new additions
5 | Write code whilst testing to implement new features
2 | Write comments highlighting updated/new sections of code
2 | Upload executable on website
2 | Ensure code can be inserted in the zipfile
Final Architecture and Traceability report
4 | Review current requirements against current architecture
3 | Propose Changes
3 | Finalise changes
4 | Restructure UML
Evaluation and Testing Report
3 | Analyse the brief and make bullet points of key points
3 | Reanalyse requirements
4 | Check that the game meets each point in the brief and all the requirements
5 | Prepare a list of core tests that are done each time a significant change is implemented
4 | Systematically test code throughout implementation
2 | Create logs of test results
2 | Create a graph of test results over time
Project Review Report
3 | Analyse current team management methods
4 | Review management methods against initial management methods
3 | Analyse how changes in requirements and risks affected team management
2 | Review changes in tools used and report on why
3 | Review changes in development methods used
4 | Write a short report on changes in our understanding of software engineering
5 | Update Website